## Main
Scrum Project
Product |  |  | Product Status
Active versions |  |  | Sponsor
Team
Scrum Master |  |  | Product Owner
Developers |  |  | Project Champion
Other Stakeholders
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | Spr. 1.1 | 2019-01-07 | 2019-01-18 | Complete | 22 | 20
[6 empty] | Spr. 1.2 | 2019-01-21 | 2019-02-01 | Complete | 20 | 23
[6 empty] | Spr. 1.3 | 2019-02-04 | 2019-02-15 | Complete | 19 | 15
[6 empty] | Spr. 1.4 | 2019-02-18 | 2019-03-01 | Complete | 25 | 27
[6 empty] | Spr. 1.5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 | product | customer | register my product | I can sell my product | (Given)a customer must create account in our app. (When)Input the product attribute and click on submit button.(Then) The product be post in system
2 | product | customer | search for product | I can find my favorite product | a customer must create account in our app(Given). Enter the product name and click on search button(When). System must show prudoct if exests(Then)
3 | product | customer | buy the product | I buy the product I need to | a customer must create account in our app(Given). Product choiced by customer(When). customer call to product owner for buy product (Then)
4 | category | customer | add my product to type of category | all product will organized | (Given)Every product must assign to it's related category.(When)product shuld take a spicific type. (Then) all product shuld organized by it's own categories and types
5 | locaiton | customer | save my product location | buyir can find me easily | (Given) product must be existed.(when) add location to product.(then) location should submited
6 | search | customer | search product | I can find the product I looks for | (given) customer sould chose (category or location). (when) customer must enter the product name.(then) customer should chose item
7 | message | customer | send message to seller | I can get more information about product from seller | (given) See and choose product.(when)customer should loging in application. (then)Send message to seller
8 | message | customer | recive message from buyer | I can sell my product | (Given) recive message from buyer.(when) seller reply to buyer.(then) buyer should recive deitails about procuct
9 | Ranking | customer | rate customer profile | others know that customer is trustworthy or not | (Given) customer sould have account.(when) enter amount of stars. (then) customer can see amount of rating
10 | suggestion | customer | suggest my idea to develoopers | I can help developers to sovle their probloms and add more functionlity to app | (Given) should login in application.(when) suggest idea or problems .(then) system recive suggestion and show to devolepers
11 | help center | admin | provide help center to user | can help customer to solve their probloms | while user have problem in using of app . customer should call to help center for more info . Help center should response .
12 | add new admin | admin | add new admin to my website | to solove user problomes faster | while a user selected as admin . It should have full prevelge to all app , so that admin can make full changes in app.
13 | block | admin | block customer | clean my website from scamer | while an ilegal is done. I should resive a report. then I should block customer for some time
14 | edit | customer | edit post or product details | give exact info of product and solve errors of info | (Given) click on edit (When) update and submit info (Then) system save the new info
15 | edit | customer | edit profile info | update info about my self | (Given) customer should login and click on profile edit (Whem) update info (Then) save updates
16 | delete | customer | delete post | prevent from others to see my post | (Given) click on delete (When) get confirmation to delete (Then) remove post from system

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 |  |  |  | 8 | 2 | 6 | 1 |  | 1
1.1 | 224 |  |  |  | 2 | 1 | 1 |  | 1
1.1 | 225 |  |  |  | 5 | 5 | 0 |  | 1 |  | 2 |  | 1 | 1
1.1 | 229 |  |  |  | 3 | 3 | 0 |  |  | 1 |  | 1 |  |  | 1
1.1 | 251 |  |  |  | 13 | 13 | 0 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1.1 | 253 |  |  |  | 1 | 1 | 0 | [9 empty] | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 32 | 25 | 7 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | 28 | 24 | 21 | 18 | 16 | 14 | 12 | 10 | 9 | 7
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms